{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["年度项目库 (2026)"],"not_rendered":{"defined_names":1},"read":"whole","date_system":"1900"}

{"sheet":"年度项目库 (2026)","index":0,"n_rows":82,"n_cols":26,"rows_kept":82,"merged":[[0,0,0,25],[1,0,1,2],[1,23,1,25],[2,0,4,0],[2,1,2,3],[2,4,4,4],[2,5,4,5],[2,6,4,6],[2,7,4,7],[2,8,4,8],[2,9,2,10],[2,11,4,11],[2,12,4,12],[2,13,4,13],[2,14,2,16],[2,17,4,17],[2,18,4,18],[2,19,2,24],[2,25,4,25],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,9,4,9],[3,10,4,10],[3,14,4,14],[3,15,3,16],[3,19,4,19],[3,20,4,20],[3,21,4,21],[3,22,3,24],[5,0,5,25],[35,0,35,25],[45,0,45,25],[78,0,78,25]]}
["左云县2026年度巩固拓展脱贫攻坚成果和乡村振兴项目拟实施计划清单"]
[]
["序号","项目类别",null,null,"乡镇","村","项目名称","建设性质","实施地点","实施期限",null,"责任单位","实施单位及责任人","建设内容及规模","资金来源及规模",null,null,"绩效目标","联农带农机制","受益对象",{"$nulls":5},"备注"]
[null,"项目类型","二级项目类型","项目子类型",{"$nulls":5},"计划开\n工时间","计划完\n工时间",{"$nulls":3},"预算\n总投资\n（万元）","其中",{"$nulls":3},"受益\n村数（个）","受益\n户数（户）","受益\n人口数\n（人）","其中"]
[{"$nulls":15},"财政资金\n（万元）","其他资金\n（万元）",{"$nulls":5},"受益脱贫村数（个）","受益脱贫户数及防止返贫监测对象户数（户）","受益脱贫人口数及防止返贫监测对象人口数（人）"]
["产业发展（3459.15 万元）"]
[1,"产业发展","生产项目","种植业基地","左云县",null,"左云县粮食产地机械化烘干设施建设及应急救援体系试点项目","新建","左云县","2026-03-01","2026-11-01","现代农业服务中心","现代农业服务中心\n张国伟","建设机械化烘干中心1个",240,240,null,"建立平急两用的粮食产地烘干体系，发挥设施装备对粮食生产防灾减损的支撑作用","提升村民粮食产量，改善村民生活质量",9,1800,2400,2]
[2,"产业发展","生产项目","种植业基地","左云县",null,"左云县粮油作物农机化提质增效技术推广示范项目","新建","左云县","2026-03-01","2026-11-01","现代农业服务中心","现代农业服务中心\n张国伟","生产全程机械化技术示范，引进先进适用的农机具，大力发展农业机械现代化",100,100,null,"提升和引领不同农作物机械化能力、水平，促进粮食增产、农民增收","提升村民粮食产量，改善村民生活质量",12]
[3,"产业发展","生产项目","种植业基地","左云县",null,"左云县农产品加工机械化提质增效项目","新建","左云县","2026-03-01","2026-11-01","现代农业服务中心","现代农业服务中心\n张国伟","购置加工装备，开展技术培训观摩演示会",40,40,null,"进一步提升粮食加工向精细化发展","提升加工效率，解决群众加工需求",5,1000,2500,1]
[4,"产业发展","生产项目","种植业基地","左云县",null,"左云县有机旱作膜下滴灌项目","新建","左云县","2026-03-01","2026-11-01","现代农业服务中心","现代农业服务中心\n付成权","3万余亩农作物运用膜下滴灌",300,300,null,"提升农业生产综合能力，促进粮食增产、农民增收","带动村民粮食生产持续增产增效"]
[5,"产业发展","生产项目","种植业基地","左云县",null,"左云县大豆玉米带状复合种植项目","新建","左云县","2026-03-01","2026-11-01","现代农业服务中心","现代农业服务中心\n付成权","1万余亩大豆玉米带状复合种植",100,100,null,"提高农作物产量，增加农民收入","提高农作物亩产量，促进农业增效和农民增收"]
[6,"产业发展","生产项目","养殖业基地","左云县",null,"2026“雁云白羊”新品种培育核心育种场项目","新建","左云县","2026-03-02","2026-11-02","现代农业服务中心","现代农业服务中心\n付成权","新品种培育",240,240,null,"改善养殖品种，提高农民产出","促进农业增效和农民增收"]
[7,"产业发展","生产项目","养殖业基地","左云县",null,"2026年左云县优质种羊推广项目","新建","左云县","2026-03-03","2026-11-03","现代农业服务中心","现代农业服务中心\n付成权","绒山羊100只，棉羊500只",300,300,null,"改善养殖品种，提高农民产出","促进农业增效和农民增收"]
[8,"产业发展","生产项目","种植业基地","左云县",null,"左云县地膜科学回收试点项目","新建","左云县","2026-03-03","2026-11-03","现代农业服务中心","现代农业服务中心付成权","推广应用全生物降解地膜 40000亩，每亩补贴60元",240,240,null,"减少污染，改善农业生产生态环境","有效调动农民积极性，提升地膜 回收水平 "]
[9,"产业发展","生产项目","种植业基地","鹊儿山镇","郭奉窑村","左云县鹊儿山镇郭奉窑村特色经济林栽植管护项目","新建","郭奉窑村","2026-03-01","2026-11-01","鹊儿山镇","郭奉窑村郝海生","15亩果树的栽植任务",40.5,40.5,null,"壮大村集体经济，提高种植效益","提高种植效益，带动脱贫户增收入",1,51]
[10,"产业发展","产业服务支撑项目","农业社会化服务","左云县",null,"左云县植保无人机飞防补贴项目","新建","左云县","2026-03-01","2026-11-01","现代农业服务中心","现代农业服务中心\n张国伟","给使用无人机的农户实施奖补",30,30,null,"推动农作物生产机械化技术应用","服务广大分散种植户，减轻劳动强度",6,6]
[11,"产业发展","生产项目","光伏电站建设","三屯乡",null,"左云县三屯乡2019年-2020年户用光伏发电2026年度电价补贴","新建","各村","2026-01-01","2026-11-01","三屯乡","三屯乡\n刘海珍","为脱贫户户用光伏发电2026年度电价差价进行补贴",15,15,null,"为脱贫户增加收入","带动脱贫户增收",16,171,171]
[12,"产业发展","生产项目","光伏电站建设","管家堡乡",null,"左云县管家堡乡2019年-2020年户用光伏发电2026年度电价补贴","新建","各村","2026-01-01","2026-11-01","管家堡乡","管家堡乡白彬","为脱贫户户用光伏发电2026年度电价差价进行补贴",23,23,null,"为脱贫户增加收入","带动脱贫户增收",16,342,620]
[13,"产业发展","生产项目","光伏电站建设","云兴镇",null,"左云县云兴镇户用光伏发电2026年度电价补贴项目","新建","各村","2026-01-01","2026-11-01","云兴镇","云兴镇\n胡利文","为脱贫户户用光伏发电2026年度电价差价进行补贴",14,14,null,"为脱贫户增加收入","带动脱贫户增收",20,130,130]
[14,"产业发展","生产项目","光伏电站建设","张家场乡",null,"左云县张家场乡2020年户用光伏发电2026年度电价补贴项目","新建","各村","2026-01-01","2026-11-01","张家场乡","张家场乡李超","为脱贫户户用光伏发电2026年度电价差价进行补贴",15,15,null,"增加脱贫户收入","带动脱贫户增收",19,206,448,null,206,448]
[15,"产业发展","生产项目","光伏电站建设","马道头乡",null,"左云县马道头乡2020年户用光伏发电2026年度电价补贴","新建","各村","2026-03-01","2026-11-01","马道头乡","马道头乡\n王德强","为脱贫户户用光伏发电2026年度电价差价进行补贴",10,10,null,"为脱贫户增加收入","带动脱贫户增收",10,104,202,null,104,202]
[16,"产业发展","生产项目","光伏电站建设","小京庄乡",null,"左云县小京庄乡户用光伏发电2026年度电价补贴项目","新建","各村","2026-01-01","2026-11-01","小京庄乡","小京庄乡\n辛振栋","为脱贫户户用光伏发电2026年度电价差价进行补贴",8,8,null,"为脱贫户增加收入","带动脱贫户增收",7,118,235,7,51,101]
[17,"产业发展","加工流通项目","加工业","鹊儿山镇","小破堡村","2026年鹊儿山镇小破堡村杂粮烘干项目","新建","小破堡村","2026-03-01","2026-11-01","鹊儿山镇","小破堡村李连锁","新建厂房、地面硬化、及购置粮食烘干机器",70,70,null,"带动周边脱贫劳动力就业、增加村集体经济","带动周边脱贫户和监测户对象稳定就业",1,659,1519,1,51,136]
[18,"产业发展","加工流通项目","加工业","马道头乡","高庙村","马道头乡高庙村柠条加工项目","新建","高庙村","2026-03-01","2026-11-01","马道头乡","高庙村\n贾勇\n","建设占地20亩柠条加工厂，购置设备、采购原材料",300,300,null,"发展壮大村集体经济\n","增加全体农户收入，解决脱贫户、监测户就业\n",1,75,126,null,15,30]
[19,"产业发展","加工流通项目","加工业","小京庄乡","酸茨河村","左云县小京庄乡酸茨河村豆制品加工厂项目","新建","酸茨河村","2026-03-01","2026-11-01","小京庄乡","酸茨河村\n郑京伟","新建豆制品加工厂，组建生产线，购买设备及搭配纯净水生产",250,250,null,"满足当地及周边对豆制品的需求、增加当地农民的收入，促进农村经济发展、吸引农村剩余劳动力就业，提高当地农民的收入水平和生活质量","壮大村集体经济，带动脱贫人口的收入增加，提供就业岗位",1,76,156,null,0,0]
[20,"产业发展","加工流通项目","加工业","小京庄乡","上下泥河村","左云县小京庄乡上下泥河村卫生纸加工项目","新建","上下泥河村","2026-03-01","2026-11-01","小京庄乡","上下泥河村\n徐杰","新建卫生纸加工厂，购买卫生纸自动复卷机、切割机、包装机",45,45,null,"壮大集体经济，提供就业岗位，增加当地农民收入","壮大集体经济，提高整体经济水平，带动脱贫人口的收入增加，提供就业岗位",1,83,144,1,62,110]
[21,"产业发展","加工流通项目","加工业","云兴镇","南关村","左云县南关粮食仓储烘干厂建设项目","新建","南关村","2026-03-01","2026-11-01","云兴镇","南关村\n宋利军 ","建设粮食储藏和烘干厂房，购置粮食烘干设备",500,500,null,"提升粮食处理能力","带动周边农民种植积极性，提高农民收入",1,null,658,null,35]
[22,"产业发展","加工流通项目","加工业","云兴镇","南京庄","左云县云兴镇南京庄（杜村）粮食仓储烘干厂建设项目","新建","南京庄","2026-03-01","2026-11-01","云兴镇","南京庄\n潘永成","建设粮食储藏和烘干厂房，购置粮食烘干设备",500,500,null,"提升粮食处理能力","带动周边农民种植积极性，提高农民收入",1,null,194,null,11]
[23,"产业发展","金融保险配套项目","小额贷款贴息","左云县",null,"2026年左云县小额贷款贴息项目","新建","左云县","2026-03-01","2026-11-01","乡村建设发展中心","乡村建设发展中心赵转香","为脱贫户小额信贷支付利息",50,50,null,"通过小额信贷贴息，支持脱贫户、监测户自主发展产业，解决开展经营融资难融资贵问题","发展生产，带动增收"]
[24,"产业发展","高质量庭院经济","庭院特色种植","云兴镇",null,"2026年左云县云兴镇高质量发展庭院经济项目","新建","各村","2026-03-01","2026-11-01","云兴镇","云兴镇\n胡利文","小种植小养殖发展",8.5,8.5,null,"促进农民就业创业增收，发展农村经济","增加农民收入，提高农民生活水平",null,60,null,null,60]
[25,"产业发展","高质量庭院经济","庭院特色种植","管家堡乡",null,"2026年左云县管家堡乡高质量发展庭院经济项目","新建","各村","2026-03-01","2026-11-01","管家堡乡","管家堡乡白彬","小种植小养殖发展",3,3,null,"促进农民就业创业增收，发展农村经济","增加农民收入，提高农民生活水平",null,20,null,null,20]
[26,"产业发展","高质量庭院经济","庭院特色种植","鹊儿山镇",null,"2026年左云县鹊儿山镇高质量发展庭院经济项目","新建","各村","2026-03-01","2026-11-01","鹊儿山镇","鹊儿山镇梁文君","小种植小养殖发展",4.15,4.15,null,"促进农民就业创业增收，发展农村经济","增加农民收入，提高农民生活水平",null,30,null,null,30]
[27,"产业发展","高质量庭院经济","庭院特色种植","小京庄乡",null,"2026年左云县小京庄乡高质量发展庭院经济项目","新建","各村","2026-03-01","2026-11-01","小京庄乡","小京庄乡辛振栋","小种植小养殖发展",4,4,null,"促进农民就业创业增收，发展农村经济","增加农民收入，提高农民生活水平",null,25,null,null,25]
[28,"产业发展","高质量庭院经济","庭院特色种植","马道头乡",null,"2026年左云县马道头乡高质量发展庭院经济项目","新建","各村","2026-03-01","2026-11-01","马道头乡","马道头乡王德强","小种植小养殖发展",3,3,null,"促进农民就业创业增收，发展农村经济","增加农民收入，提高农民生活水平",null,40,null,null,40]
[29,"产业发展","高质量庭院经济","庭院特色种植","张家场乡",null,"2026年左云县张家场乡高质量发展庭院经济项目","新建","各村","2026-03-01","2026-11-01","张家场乡","张家场乡李超","小种植小养殖发展",6,6,null,"促进农民就业创业增收，发展农村经济","增加农民收入，提高农民生活水平",null,50,null,null,50]
["就业项目（160万元）"]
[30,"就业项目","务工补助","交通费补助","管家堡乡",null,"2026年管家堡乡脱贫劳动力外出务工一次性交通补贴项目","新建","管家堡乡","2026-03-01","2026-11-01","管家堡乡","管家堡乡白彬","脱贫劳动力外出务工交通补贴",6,6,null,"鼓励外出务工，带动增收","提高收入，改善生活水平",null,100,null,null,100]
[31,"就业项目","务工补助","交通费补助","鹊儿山镇",null,"2026年鹊儿山镇脱贫劳动力外出务工一次性交通补贴项目","新建","鹊儿山镇","2026-03-01","2026-11-01","鹊儿山镇","鹊儿山镇梁文君","脱贫劳动力外出务工交通补贴",11,11,null,"鼓励外出务工，带动增收","提高收入，改善生活水平",null,150,null,null,150]
[32,"就业项目","务工补助","交通费补助","张家场乡",null,"2026年张家场乡脱贫劳动力外出务工一次性交通补贴项目","新建","张家场乡","2026-03-01","2026-11-01","张家场乡","张家场乡李超","脱贫劳动力外出务工交通补贴",6,6,null,"鼓励外出务工，带动增收","提高收入，改善生活水平",null,100,null,null,100]
[33,"就业项目","务工补助","交通费补助","三屯乡",null,"2026年三屯乡脱贫劳动力外出务工一次性交通补贴项目","新建","三屯乡","2026-03-01","2026-11-01","三屯乡","三屯乡\n刘海珍","脱贫劳动力外出务工交通补贴",4,4,null,"鼓励外出务工，带动增收","提高收入，改善生活水平",null,65,null,null,65]
[34,"就业项目","务工补助","交通费补助","云兴镇",null,"2026年云兴镇脱贫劳动力外出务工一次性交通补贴项目","新建","云兴镇","2026-03-01","2026-11-01","云兴镇","云兴镇\n胡利文","脱贫劳动力外出务工交通补贴",2,2,null,"鼓励外出务工，带动增收","提高收入，改善生活水平",null,30,null,null,30]
[35,"就业项目","务工补助","交通费补助","马道头乡",null,"2026年马道头乡脱贫劳动力外出务工一次性交通补贴项目","新建","马道头乡","2026-03-01","2026-11-01","马道头乡","马道头乡\n王德强","脱贫劳动力外出务工交通补贴",1,1,null,"鼓励外出务工，带动增收","提高收入，改善生活水平",null,17,null,null,17]
[36,"就业项目","务工补助","交通费补助","小京庄乡",null,"2026年小京庄乡脱贫劳动力外出务工一次性交通补贴项目","新建","小京庄乡","2026-03-01","2026-11-01","小京庄乡","小京庄乡\n辛振栋","脱贫劳动力外出务工交通补贴",9,9,null,"鼓励外出务工，带动增收","提高收入，改善生活水平",null,120,null,null,120]
[37,"就业项目","务工补助","交通费补助","店湾镇",null,"2026年店湾镇脱贫劳动力外出务工一次性交通补贴项目","新建","店湾镇","2026-03-01","2026-11-01","店湾镇","店湾镇\n刘宏宇","脱贫劳动力外出务工交通补贴",23,23,null,"鼓励外出务工，带动增收","提高收入，改善生活水平",null,300,null,null,300]
[38,"就业项目","务工补助","生产奖补、劳务补助等","左云县",null,"2026年左云县脱贫劳动力外出务工就业和帮扶车间务工就业一次性稳岗补助项目","新建","左云县","2026-03-01","2026-11-01","人社局","人社局\n刘波","脱贫劳动力外出务工稳岗补助",98,98,null,"提高农民收入","提高农民收入，改善生活水平",null,500,null,null,500]
["乡村建设行动（3534万元）"]
[39,"乡村建设行动","农村基础设施（含产业配套基础设施）","产业路、资源路、旅游路建设","张家场乡","大堡角村","2026年大堡角村产业路建设项目","新建","大堡角村","2026-03-01","2026-11-01","大堡角村","大堡角村姚建云","产业路建设1公里",100,100,null,"改善生产生活条件","提高生产效率，促进农民增收",1,229,null,null,74]
[40,"乡村建设行动","农村基础设施（含产业配套基础设施）","农村供水保障设施建设","管家堡乡","曹家窑村","左云县管家堡乡曹家窑村\n农村供水巩固提升项目","新建","管家堡乡\n曹家窑","2026-05-01","2026-11-01","\n曹家窑村","曹家窑村\n白  彬","自来水入户改造",150,150,null,"饮水安全巩固提升,改善人居环境","改善群众生产生活条件，全面推进乡村振兴",1]
[41,"乡村建设行动","农村基础设施（含产业配套基础设施）","农村供水保障设施建设","云兴镇","赵火色","左云县云兴镇赵火色\n农村供水巩固提升项目","新建","云兴镇\n赵火色","2026-05-01","2026-11-01","\n赵火色村","赵火色村赵振岳","自来水入户改造",80,80,null,"饮水安全巩固提升,改善人居环境","改善群众生产生活条件，全面推进乡村振兴",1]
[42,"乡村建设行动","农村基础设施（含产业配套基础设施）","农村供水保障设施建设","张家场乡","猪儿洼","左云县张家场乡猪儿洼\n农村供水巩固提升项目","新建","张家场乡猪儿洼","2026-05-01","2026-11-01","猪儿洼村","猪儿洼村胡五元","修建水源，自来水入户改造更新",220,220,null,"饮水安全巩固提升,改善人居环境","改善群众生产生活条件，全面推进乡村振兴",1]
[43,"乡村建设行动","农村基础设施（含产业配套基础设施）","农村供水保障设施建设","张家场乡","小厂子","左云县张家场乡小厂子\n农村供水巩固提升项目","新建","张家场乡小厂子","2026-05-01","2026-11-01","小厂子村","小厂子村张利红","自来水入户改造",140,140,null,"饮水安全巩固提升,改善人居环境","改善群众生产生活条件，全面推进乡村振兴",1]
[44,"乡村建设行动","农村基础设施（含产业配套基础设施）","农村供水保障设施建设","云兴镇\n三屯乡\n张家场乡\n管家堡乡","10个村","左云县2026年农村供水保障维修养护建设项目","维修","10个村","2026-05-01","2026-11-01","左云县农业农村和水务局","农业农村和水务局\n周斌","维修养护水利设施",130,130,null,"饮水安全巩固提升,改善人居环境","改善群众生产生活条件，全面推进乡村振兴",10,null,2437]
[45,"乡村建设行动","农村基础设施（含产业配套基础设施）","农村供水保障设施建设","小京庄乡\n马道头乡\n三屯乡\n张家场乡\n管家堡乡\n店湾镇\n云兴镇","47个村","左云县2026年农村供水水质提升建设项目","新建","47个村","2026-05-01","2026-11-01","左云县农业农村和水务局","农业农村和水务局\n周斌","保障农村饮用水水质，为47个村配置消毒设施",390,390,null,"饮水安全巩固提升,改善人居环境","改善群众生产生活条件，全面推进乡村振兴",47,null,7062]
[46,"乡村建设行动","农村基础设施（含产业配套基础设施）","农村供水保障设施建设","管家堡乡","平川","左云县农村供水巩固提升项目（平川）","新建","管家堡乡\n平川","2026-05-01","2026-11-01","管家堡乡\n平川","\n平川村村崔存丽","修建水源，自来水入户改造更新",210,210,null,"饮水安全巩固提升,改善人居环境","改善群众生产生活条件，全面推进乡村振兴",1]
[47,"乡村建设行动","农村基础设施（含产业配套基础设施）","农村供水保障设施建设","管家堡乡","廖家堡","左云县农村供水巩固提升项目（廖家堡）","新建","管家堡乡\n廖家堡","2026-05-01","2026-11-01","管家堡乡\n廖家堡","\n廖家堡村徐利福","修建水源，自来水入户改造更新",210,210,null,"饮水安全巩固提升,改善人居环境","改善群众生产生活条件，全面推进乡村振兴",1]
[48,"乡村建设行动","农村基础设施（含产业配套基础设施）","农村供水保障设施建设","管家堡乡","太平墩","左云县农村供水巩固提升项目（六队）","新建","管家堡乡\n太平墩","2026-05-01","2026-11-01","管家堡乡\n太平墩","\n太平墩村\n马建芳","修建水源，自来水入户改造更新",100,100,null,"饮水安全巩固提升,改善人居环境","改善群众生产生活条件，全面推进乡村振兴",1]
[49,"乡村建设行动","农村基础设施（含产业配套基础设施）","农村供水保障设施建设","三屯乡","段家村","左云县农村供水巩固提升项目（段家村）","新建","三屯乡\n段家村","2026-05-01","2026-11-01","三屯乡\n段家村","\n段家村\n刘延续","修建水源，自来水入户改造更新",310,310,null,"饮水安全巩固提升,改善人居环境","改善群众生产生活条件，全面推进乡村振兴",1]
[50,"乡村建设行动","农村基础设施（含产业配套基础设施）","农村供水保障设施建设","三屯乡","鹊儿河","左云县农村供水巩固提升项目（鹊儿河）","新建","三屯乡\n鹊儿河","2026-05-01","2026-11-01","三屯乡\n鹊儿河","\n鹊儿河村武国龙","修建水源，自来水入户改造更新",100,100,null,"饮水安全巩固提升,改善人居环境","改善群众生产生活条件，全面推进乡村振兴",1]
[51,"乡村建设行动","农村基础设施（含产业配套基础设施）","农村供水保障设施建设","三屯乡","鹊儿河","左云县农村供水巩固提升项目（范家坟）","新建","三屯乡\n鹊儿河","2026-05-01","2026-11-01","三屯乡\n鹊儿河","\n鹊儿河\n武国龙","修建水源，自来水入户改造更新",55,55,null,"饮水安全巩固提升,改善人居环境","改善群众生产生活条件，全面推进乡村振兴",1]
[52,"乡村建设行动","农村基础设施（含产业配套基础设施）","农村供水保障设施建设","小京庄乡","小堡子","左云县农村供水巩固提升项目（小堡子）","新建","小京庄乡\n小堡子","2026-05-01","2026-11-01","小京庄乡\n小堡子","\n小堡子\n李耀","修建水源，自来水入户改造更新",180,180,null,"饮水安全巩固提升,改善人居环境","改善群众生产生活条件，全面推进乡村振兴",1]
[53,"乡村建设行动","农村基础设施（含产业配套基础设施）","农村供水保障设施建设","小京庄乡","太堡寨","左云县农村供水巩固提升项目（向阳寨）","新建","小京庄乡\n向阳寨","2026-05-01","2026-11-01","小京庄乡\n向阳寨","\n向阳寨村朱有","修建水源，自来水入户改造更新",80,80,null,"饮水安全巩固提升,改善人居环境","改善群众生产生活条件，全面推进乡村振兴",1]
[54,"乡村建设行动","农村基础设施（含产业配套基础设施）","农村供水保障设施建设","张家场乡","长城岭","左云县农村供水巩固提升项目（长城岭）","新建","张家场乡\n长城铃","2026-05-01","2026-11-01","张家场乡\n长城铃","\n长城铃村窦贵生","修建水源，自来水入户改造更新",110,110,null,"饮水安全巩固提升,改善人居环境","改善群众生产生活条件，全面推进乡村振兴",1]
[55,"乡村建设行动","农村基础设施（含产业配套基础设施）","农村供水保障设施建设","管家堡乡","金家沟村","左云县管家堡乡金家沟村管道维修项目","新建","金家沟村","2026-05-01","2026-11-01","管家堡乡","金家沟村\n张翠云","吃水井变频柜及管道维修",2,2,null,"饮水安全巩固提升,改善人居环境","改善群众生产生活条件，全面推进乡村振兴",1,48,119,null,28,70]
[56,"乡村建设行动","农村基础设施（含产业配套基础设施）","农村供水保障设施建设","管家堡乡","东辛村","左云县管家堡乡东辛村农村供水巩固提升项目","新建","东辛村","2026-05-01","2026-11-01","管家堡乡","东辛村\n巴红卫","打自来水井一口及安装水表",20,20,null,"饮水安全巩固提升,改善人居环境","改善群众生产生活条件，全面推进乡村振兴",1,46,75,null,17,30]
[57,"乡村建设行动","农村基础设施（含产业配套基础设施）","农村供水保障设施建设","云兴镇","张祥村","左云县云兴镇张祥村（刘家窑村）农村供水巩固提升项目","新建","张祥村","2026-05-01","2026-11-01","张祥村","张祥村\n刘三人","修建水源，自来水入户改造更新",30,30,null,"饮水安全巩固提升,改善人居环境","改善群众生产生活条件",1,null,134,null,null,3]
[58,"乡村建设行动","人居环境整治","村容村貌提升","店湾镇","各村","左云县管家堡乡人居环境整治项目","新建","店湾镇","2026-03-01","2026-11-01","店湾镇","店湾镇\n刘宏宇","改善人居环境",60,60,null,"人居环境提升","提升村民生活环境，增加就业岗位",2,825,2113,null,127,221]
[59,"乡村建设行动","人居环境整治","村容村貌提升","鹊儿山镇","各村","左云县鹊儿山镇人居环境整治项目","新建","鹊儿山镇","2026-03-01","2026-11-01","鹊儿山镇","鹊儿山镇梁文君","用于环境治理",18,18,null,"人居环境提升","带动周边脱贫户就业及脱贫村增收",8,977,1912,2,104,273]
[60,"乡村建设行动","人居环境整治","村容村貌提升","管家堡乡","各村","左云县张家场乡人居环境整治项目","新建","管家堡乡","2026-03-01","2026-11-01","管家堡乡","管家堡乡白彬","改善人居环境",48,48,null,"人居环境提升","改善群众生产生活条件",17,1615,3120]
[61,"乡村建设行动","人居环境整治","村容村貌提升","云兴镇","各村","左云县三屯乡人居环境整治项目","新建","云兴镇","2026-03-01","2026-11-01","云兴镇","云兴镇\n胡利文","改善人居环境",44,44,null,"人居环境提升","改善群众生产生活条件",17]
[62,"乡村建设行动","人居环境整治","村容村貌提升","张家场乡","各村","左云县云兴镇人居环境整治项目","新建","张家场乡","2026-03-01","2026-11-01","张家场乡","张家场乡李超","改善人居环境",30,30,null,"人居环境提升","提升村民生活环境，增加就业岗位",24,3000,3000,null,206,448]
[63,"乡村建设行动","人居环境整治","村容村貌提升","马道头乡","各村","左云县马道头乡人居环境整治项目","新建","马道头乡","2026-03-01","2026-11-01","马道头乡","马道头乡王德强","改善人居环境",38,38,null,"人居环境提升","改善农村人居环境，提高农民生活质量",17]
[64,"乡村建设行动","人居环境整治","村容村貌提升","小京庄乡","各村","左云县小京庄乡人居环境整治项目","新建","小京庄乡","2026-03-01","2026-11-01","小京庄乡","小京庄乡辛振栋","改善人居环境",38,38,null,"人居环境提升","整治人居环境，提高生活质量",23,1770,3385,11,647,1298]
[65,"乡村建设行动","人居环境整治","村容村貌提升","三屯乡","各村","左云县店湾镇人居环境整治项目","新建","三屯乡","2026-03-01","2026-11-01","三屯乡","三屯乡\n刘海珍","改善人居环境",24,24,null,"人居环境提升","改善群众生产生活条件",17,null,null,3]
[66,"乡村建设行动","人居环境整治","村容村貌提升","马道头乡","上石岔村","左云县马道头乡上石岔村村庄整治项目","新建","上石岔村","2026-03-01","2026-11-01","马道头乡","上石岔村陈日胜","改善人居环境",70,70,null,"人居环境提升","整治人居环境，提高生活质量",1,null,659,null,18]
[67,"乡村建设行动","人居环境整治","村容村貌提升","马道头乡","马道头村","左云县马道头乡马道头村村庄整治项目","新建","马道头村","2026-03-01","2026-11-01","马道头乡","马道头村石应栋","改善人居环境",160,160,null,"人居环境提升","整治人居环境，提高生活质量",1,null,941,null,34]
[68,"乡村建设行动","人居环境整治","村容村貌提升","马道头乡","高庙村","左云县马道头乡高庙村村庄整治项目","新建","高庙村","2026-03-01","2026-11-01","马道头乡","高庙村\n贾勇","改善人居环境",125,125,null,"人居环境提升","整治人居环境，提高生活质量",1,null,598,null,27]
[69,"乡村建设行动","人居环境整治","村容村貌提升","马道头乡","下石岔村","左云县马道头乡下石岔村道路维修项目","新建","下石岔村","2026-03-01","2026-11-01","马道头乡","下石岔村郭世财","改善人居环境",137,137,null,"人居环境提升","整治人居环境，提高生活质量",1,null,718,null,20]
[70,"乡村建设行动","人居环境整治","村容村貌提升","马道头乡","鹊儿岭村","左云县马道头乡鹊儿岭村村庄整治项目","新建","鹊儿岭村","2026-03-01","2026-11-01","马道头乡","鹊儿岭村张海祥","改善人居环境",125,125,null,"人居环境提升","整治人居环境，提高生活质量",1,null,297,null,28]
["巩固三保障（69万元）"]
[71,"巩固三保障成果","教育","享受“雨露计划”职业教育补助","左云县",null,"左云县2025—2026学年雨露计划教育扶贫补助项目","新建","各乡镇","2026-03-01","2026-06-01","乡村建设发展中心","乡村建设发展中心徐向有","资助建档立卡贫困学生，每人3000元",24,24,null,"提供教育资助，确保其顺利完成学业","惠及脱贫户和监测对象困难家庭",null,80,80]
[72,"巩固三保障成果","教育","其他教育类项目","左云县",null,"2026年左云县本科大学新生资助项目","新建","各乡镇","2026-07-01","2026-09-01","乡村建设发展中心","乡村建设发展中心徐向有","资助二本B类以上建档立卡贫困大学生，一次性补助每人5000元",5,5,null,"资助考取二本B类以上建档立卡贫困大学生完成学业","惠及脱贫户和监测对象困难家庭",null,10,10]
[73,"巩固三保障成果","综合保障","防贫保险（基金）","左云县",null,"2026年左云县防贫保险基金项目","新建","各乡镇","2026-01-01","2026-06-01","乡村建设发展中心","乡村建设发展中心徐向有","为建档立卡脱贫人口购买人身意外保险、返贫保险，为监测对象购买晋惠保医疗保险",40,40,null,"确保病有所医，防止因病因灾返贫","保障脱贫户（监测对象）利益",145,2869,5264,16,2869,5264]